## Team_Mapping
Batch | Team | Member Name | Role | Week | Scrum Master?
Batch 1 | Team 1 | Mahesh | DevOps Engineer | Week 1 | No
Batch 1 | Team 1 | Aswin | DevOps Engineer | Week 1 | No
Batch 1 | Team 1 | Sowrabh Kumar | DevOps Engineer | Week 1 | No
Batch 1 | Team 1 | Elzabeth | DevOps Engineer | Week 1 | No
Batch 1 | Team 1 | Praveen Eswar | DevOps Engineer | Week 1 | No
Batch 1 | Team 1 | Surya | DevOps Engineer | Week 1 | Yes

## Sprint-Overview
Sprint | Sprint Goal | Start Date | End Date | Deliverable
1 | Understood cloud computing basics and why cloud is used. | 2026-05-06 | 2026-05-07 | We explored the fundamentals of cloud computing, understood and compared the architectural differences between AWS and Azure
2 | Explored Azure networking, public IP allocation, DHCP, and VM connectivity. | 2026-05-08 | 2026-05-09 | Created a public VM in Azure using both UI and Terraform and exposed a simple application to the internet, and understood DHCP and public IP allocation.
3 | Explored Azure VNet, network architecture, and Bastion host. | 2026-05-11 | 2026-05-12 | Built a custom network in Azure with RG, VNet, subnets, and VMs, exposed a private subnet app using a load balancer (UI + Terraform), and accessed private VM using Azure Bastion.

## Task_Tracking(23-02)
Sprint | Team | TaskID | Description | AssignedTo | StoryPoint | Status | Reviewer
1 | Team1 | T1-001 | Understood cloud computing basics and why cloud is used. | Mahesh | 5 | Done
1 | Team1 | T1-002 | Understood cloud computing basics and why cloud is used. | Aswin | 5 | Done |  | Backlog
1 | Team1 | T1-003 | Understood cloud computing basics and why cloud is used. | Sowrabh Kumar | 5 | Done
1 | Team1 | T1-004 | Understood cloud computing basics and why cloud is used. | Elzabeth | 5 | Done |  | To Do
1 | Team1 | T1-005 | Understood cloud computing basics and why cloud is used. | Praveen Eswar | 5 | Done
1 | Team1 | T1-006 | Understood cloud computing basics and why cloud is used. | Surya | 5 | Done |  | In Progress
2 | Team1 | T1-007 | Explored Azure networking basics including IP allocation, DHCP, and VM connectivity. | Mahesh | 4 | Done
2 | Team1 | T1-008 | Explored Azure networking basics including IP allocation, DHCP, and VM connectivity. | Aswin | 4 | Done |  | Code Review
2 | Team1 | T1-009 | Explored Azure networking basics including IP allocation, DHCP, and VM connectivity. | Sowrabh Kumar | 4 | Done
2 | Team1 | T1-010 | Explored Azure networking basics including IP allocation, DHCP, and VM connectivity. | Elzabeth | 4 | Done |  | Done
2 | Team1 | T1-011 | Explored Azure networking basics including IP allocation, DHCP, and VM connectivity. | Praveen Eswar | 4 | Done
2 | Team1 | T1-012 | Explored Azure networking basics including IP allocation, DHCP, and VM connectivity. | Surya | 4 | Done |  | Blocked
3 | Team1 | T1-013 | Understood Azure networking with VNet, architecture, and Bastion host. | Mahesh | 4 | Done
3 | Team1 | T1-014 | Understood Azure networking with VNet, architecture, and Bastion host. | Aswin | 4 | Done
3 | Team1 | T1-015 | Understood Azure networking with VNet, architecture, and Bastion host. | Sowrabh Kumar | 4 | Done
3 | Team1 | T1-016 | Understood Azure networking with VNet, architecture, and Bastion host. | Elzabeth | 4 | Done
3 | Team1 | T1-017 | Understood Azure networking with VNet, architecture, and Bastion host. | Praveen Eswar | 4 | Done
3 | Team1 | T1-018 | Understood Azure networking with VNet, architecture, and Bastion host. | Surya | 4 | Done

## Sprint-Overview(Sample)
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | VM & Docker Setup | 2026-02-23 | 2026-02-21 | App running in Docker
Sprint 2 | CI/CD Implementation | 2026-02-24 | 2026-02-28 | Working Jenkins pipeline
Sprint 3 | Terraform & Infra | 2026-03-03 | 2026-03-07 | Infra provisioned via Terraform
Sprint 4 | Kubernetes Deployment | 2026-03-10 | 2026-03-14 | App deployed in K8s

## Task_Tracking(Sample)
Sprint | Team | Task ID | Task Description | Assigned To | Story Points | Status | Reviewer
Sprint 1 | Team 1 | T1-001 | Install Ubuntu on EC2 and configure SSH | Arun Simon | 3 | Done | Trainer
Sprint 1 | Team 1 | T1-002 | Setup Git and push sample project to GitHub | Sathvik NB Math | 2 | In Progress | Arun Simon
Sprint 1 | Team 1 | T1-003 | Install Docker and run nginx container | Preethi TK | 3 | Code Review | Trainer
Sprint 1 | Team 2 | T2-001 | Launch EC2 and configure security groups | Gokul | 3 | Done | Trainer
Sprint 1 | Team 2 | T2-002 | Build Docker image for sample Java app | Aswin | 5 | In Progress | Gokul
Sprint 1 | Team 2 | T2-003 | Push Docker image to DockerHub | Johaan | 2 | To Do | -
Sprint 1 | Team 3 | T3-001 | Setup Jenkins on EC2 | Neeraj | 5 | Blocked | Trainer
Sprint 1 | Team 3 | T3-002 | Create basic CI pipeline (Build Stage) | Jayadev | 5 | In Progress | Neeraj
Sprint 1 | Team 4 | T4-001 | Write Terraform script to create EC2 | Chriss Philip Saji | 8 | To Do | Trainer
Sprint 1 | Team 4 | T4-002 | Configure remote backend for Terraform | Abhinav | 5 | Backlog | -